## Full1
Task | Who? | Estimated Time (h) | Real Time (h)
"Welcome Page" (wiki) | Jordi Oña | 1 | 2
"The Original Puzzle Bobble" (wiki) | Marc Latorre | 1 | 1
"The Sound of Puzzle Bobble" (wiki) | Fran Ruiz, Jordi Oña | 1 | 1
"The Art of Puzzle Bobble" (wiki) | Carlos Cabreira | 1 | 1
"Narrative" (wiki) | Fran Ruiz, Jordi Oña | 1 | 1
"Gameplay" (wiki) | Andreu Rojas | 1 | 1
"Level Analysis" (wiki) | Carlos Cabreira | 1 | 2
"Scores" (wiki) | Marc Latorre | 1 | 1
"2 players Mode" (wiki) | Jordi Oña | 1.5 | 2
"User Interface" | Jordi Oña | 2 | 3.5
Create Beta Release | Carlos Cabreira | 0.5 | 0.5
Create 0.5v release | Carlos Cabreira | 0.5 | 0.5
Implemented Extra Bobbles | Marc Latorre | 1 | 0.75
Solve Issue #4 | Marc Latorre | 2 | 4
Implement Win/Lose condition | Fran Ruiz | 1.5 | 2
Arrange Win/Lose condition | Jordi Oña | 2 | 2
Solve memory leaks | Marc Latorre | 1 | 1
God Mode | Carlos Cabreira | 0.5 | 0.5
Create “Next ball” | Jordi Oña | 2 | 0.5
Duplicate “Next ball” | Jordi Oña | 0.5 | 0.5
Take sprites coordinates | Andreu Rojas | 2 | 2
Arrange Sprites | Andreu Rojas | 1 | 1
Relocate Player1 | Fran Ruiz | 0.5 | 0.5
Duplicate Player | Marc Latorre | 2 | 1.5
Duplicate Board | Marc Latorre | 1.5 | 1
Solve 2nd Player conflict | Carlos Cabreira | 2 | 4
Add explosions | Carlos Cabreira | 1 | 1
Add monsters | Carlos Cabreira | 1 | 1
Create bobbles dropping | Carlos Cabreira, Andreu Rojas | 1 | 1.5
Create bobbles deleting | Jordi Oña, Marc Latorre | 1.5 | 1.5
Create Board | Jordi Oña, Andreu Rojas | 1 | 1
Solve Arrow Issue | Carlos Cabreira | 0.5 | 1
Add Arrow rotation | Carlos Cabreira | 2 | 1
Add BoardDown | Andreu Rojas, Jordi Oña | 2 | 2
Solve board Issues | Andreu Rojas | 1 | 1.5
Add dinosaur and bag sprites | Fran Ruiz | 1 | 1
Add animations to dinosaurs | Fran Ruiz | 1 | 1
Polish behaviour in animations | Fran Ruiz | 2 | 2
Add “Current ball” | Andreu Rojas | 1 | 1
Prepare background sprites | Carlos Cabreira | 1 | 1
Solve bobbles-deleting issues | Carlos Cabreira | 1 | 1.5
Polished Colliders | Carlos Cabreira | 0.5 | 0.5
Add Sound | Fran Ruiz | 1 | 1
Implement ModuleAudio | Jordi Oña | 1 | 2
Implement sounds and effects | Jordi Oña | 1 | 3
Duplicate Colliders | Fran Ruiz | 0.5 | 0.5
Random Colors in bobbles | Andreu Rojas | 1 | 1
Add Arrow and bobble shot | Carlos Cabreira | 1 | 2
Add Hurry Up animation and auto shot | Jordi Oña | 0.5 | 1
Added Win/Lose conditions | Marc Latorre | 1 | 1
Solve Win/Lose issues | Marc Latorre | 1 | 1
Bobbles animations | Jordi Oña | 0.5 | 1
Implement fade to black | Jordi Oña | 1 | 1.5
Implement input | Jordi Oña | 0.5 | 0.5
Implement Render Module | Jordi Oña | 1 | 0.5
Implemented Texture Module | Jordi Oña | 1 | 0.25
Implemented Window Module | Jordi Oña | 1 | 0.25
Name window | Marc Latorre | 0.25 | 0.1
User Interface module | Jordi Oña | 1 | 1
Start screen module | Jordi Oña | 1 | 1
Create OnCollision | Carlos Cabreira | 1 | 1.5
Implement Win/Lose sprites | Fran Ruiz | 1 | 1
Create 2 players map (disposition of the bobbles) | Fran Ruiz | 1 | 1
Solve right colliders problems | Fran Ruiz | 0.5 | 0.5
Mecanism sprites | Fran Ruiz | 1 | 1
Polish work on sprites | Fran Ruiz, Andreu Rojas | 2 | 2
| Total Hours | Estimated | Real
| Fran Ruiz | 15 | 15.5
| Carlos Cabreira | 15.5 | 20.5
| Jordi Oña | 25 | 29
| Marc Latorre | 13.25 | 13.85
| Andreu Rojas | 13 | 14