## Full1
Task | Who? | Estimated Time (h) | Real Time (h)
"Welcome Page" (wiki) | Jordi Oña | 1h | 2h
"The Original Puzzle Bobble" (wiki) | Marc Latorre | 1h | 1h
"The Sound of Puzzle Bobble" (wiki) | Fran Ruiz, Jordi Oña | 1h | 1h
"The Art of Puzzle Bobble" (wiki) | Carlos Cabreira | 1h | 1h
"Narrative" (wiki) | Fran Ruiz, Jordi Oña | 1h | 1h
"Gameplay" (wiki) | Andreu Rojas | 1h | 1h
"Level Analysis" (wiki) | Carlos Cabreira | 1h | 2h
"Scores" (wiki) | Marc Latorre | 1h | 1h
"2 players Mode" (wiki) | Jordi Oña | 1,5h | 2h
"User Interface" | Jordi Oña | 2h | 3,5h
Create Beta Release | Carlos Cabreira | 0,5 h | 0,5 h
Create 0.5v release | Carlos Cabreira | 0,5 h | 0,5 h
Solve Issue #4 | Marc Latorre | 2 h | 4h
Implement Win/Lose condition | Fran Ruiz | 1h | 1h
Arrange Win/Lose condition | Jordi Oña | 2 h | 2h
Solve memory leaks | Marc Latorre | 1h | 1h
God Mode | Carlos Cabreira | 0,5 h | 0,5 h
Create “Next ball” | Jordi Oña | 2 h | 0,5 h
Duplicate “Next ball” | Jordi Oña | 0,5h | 0,5h
Take sprites coordinates | Andreu Rojas | 2h | 2h
Arrange Sprites | Andreu Rojas | 1h | 1h
Relocate Player1 | Fran Ruiz | 0,5h | 0,5h
Duplicate Player | Marc Latorre | 1h | 1h
Solve 2nd Player conflict | Carlos Cabreira | 2h | 4h
Add explosions | Carlos Cabreira | 1h | 1h
Add monsters | Carlos Cabreira | 1h | 1h
Create bobbles dropping | Carlos Cabreira, Andreu Rojas | 1h | 1,5 h
Create bobbles deleting | Jordi Oña, Marc Latorre | 1h | 1h
Create Board | Jordi Oña, Andreu Rojas | 1h | 1h
Solve Arrow Issue | Carlos Cabreira | 0,5 h | 1h
Add Arrow rotation | Carlos Cabreira | 2h | 1h
Add BoardDown | Andreu Rojas, Jordi Oña | 2h | 2h
Solve board Issues | Andreu Rojas | 1h | 1,5h
Add dinosaur and bag sprites | Fran Ruiz | 1h | 1h
Add animations to dinosaurs | Fran Ruiz | 1h | 1h
Polish behaviour in animations | Fran Ruiz | 1h | 1h
Add “Current ball” | Andreu Rojas | 1h | 1h
Prepare background sprites | Carlos Cabreira | 1h | 1h
Solve bobbles-deleting issues | Carlos Cabreira | 1h | 1,5h
Polished Colliders | Carlos Cabreira | 0,5 h | 0,5 h
Add Sound | Fran Ruiz | 0,5h | 0,5h
Implement ModuleAudio | Jordi Oña | 1h | 2h
Implement sounds and effects | Jordi Oña | 1h | 3h
Duplicate Colliders | Fran Ruiz | 0,5h | 0,5h
Random Colors in bobbles | Andreu Rojas | 1h | 1h
Add Arrow and bobble shot | Carlos Cabreira | 1h | 2h
Add Hurry Up animation and auto shot | Jordi Oña | 0,5h | 1h
Added Win/Lose conditions | Marc Latorre | 1h | 1h
Solve Win/Lose issues | Marc Latorre | 1h | 1h
Bobbles animations | Jordi Oña | 0,5h | 1h